## Dashboard
DroneUp Post-Merger Integration — Executive Dashboard
Walmart acquisition of DroneUp · First 100 Days · ALL VALUES ARE ILLUSTRATIVE PLANNING FIGURES, not actuals. Baselines, targets and milestones are drawn from the integration plan; current readings and RAG are seeded for demonstration.
Timeline & Countdown
Close Date (Day 1) | Day 30 Gate | Day 100 Gate | Days Since Close | Days to Day 100 | 100-Day Window Elapsed
1 · North-Star KPIs — one per workstream
North-Star KPI | Workstream | Unit / Basis | Baseline (Close) | Day-100 Target | Current (illustrative) | RAG | Better Direction (drives RAG) | Day-100 Gate Criterion (plan §7)
Cost per delivery | Flight Operations | $ per delivery | 30 | 24 | 26.4 |  | Lower | Validated glidepath published; M:N pilot live
ATOMx orchestration pilot sites live | Technology & UTM | # test sites coordinating DroneUp + Wing + Zipline | 0 | 2 | 2 |  | Higher | Three operators coordinated at two sites
Key-talent retention | People & Culture | % of top ~25 critical staff retained | 100% | 90% | 96% |  | Higher | ≥90% retention of key talent
New supercenter hubs in build-out | Commercial & Stores Rollout | # hubs in physical build-out | 0 | 5 | 4 |  | Higher | 5 new hubs in build-out; DBX pilot at 2 stores
Certificate & authorisation health | Regulatory & Safety | # FAA findings or authorisation lapses | 0 | 0 | 0 |  | Lower | Zero findings; zero lapses; SMS reporting integrated
Net run-rate synergy captured | Finance & Synergies | $M recurring run-rate realised | 0 | 10 |  |  | Higher | Register 100% owner-assigned; first report issued
RAG rule: meets or beats target = Green; within 20% of target = Amber; otherwise Red. Direction column tells the formula whether higher or lower is better.
2 · Milestone Completion by Workstream
Workstream | Total Milestones | Complete | On Track | At Risk | Not Started | % Complete | RAG
Flight Operations
Technology & UTM
People & Culture
Commercial & Stores Rollout
Regulatory & Safety
Finance & Synergies
ALL WORKSTREAMS
3 · Integration Health Summary
Metric | Value | Commentary
Overall integration health |  | Amber while any Red-scored risk is open or more than two milestones are at risk.
Total milestones in the 100-day plan |  | Six workstream charters × three gates (Day 1 / Day 30 / Day 100).
Milestones complete |  | All Day-1 protect-and-stabilise milestones.
Milestone completion |  | Complete as a share of the full plan.
Average % complete (all milestones) |  | Weighted by milestone progress rather than binary completion.
Milestones at risk |  | Escalated to the IMO weekly stand-up.
Day-1 gate status |  | Day 1 = Protect. Certificate, people and platform arrive intact.
Open risks scored Red |  | Score ≥15 on the 5×5 probability/impact grid.
Highest residual risk score |  | Key-talent flight is the top-scored risk.
Recurring synergy identified ($M run-rate) |  | Excludes the one-time avoided-build-cost NPV advantage.
Net synergy after costs-to-achieve ($M) |  | All categories, annual value estimate less costs-to-achieve (retention, hub build-outs, integration engineering).
Earn-out consideration at risk ($M) |  | Allocated across five earn-out milestones; ties to the earn-out pool on the Assumptions tab.
Source: DroneUp Post-Merger Integration Plan — The First 100 Days (Walmart Corporate Development, Aug 2026), referencing DroneUp Company Profile: Strategic Fit Analysis for Walmart (May 2026). All quantities are illustrative planning values unless fixed in the plan.

## Milestone Tracker
Milestone Tracker — 100-Day Integration Plan
Master plan across the six workstream charters (plan §4). Due dates are formulas keyed to the Close Date on the Assumptions tab — they re-flow automatically if close moves.
Close Date (Day 1): |  | Day 30 Gate: |  | Day 100 Gate:
Workstream | Gate | Milestone | Owner | Due Date | Status | % Complete | Notes
Flight Operations | Day 1 | DFW Part 135 delivery operations fly without interruption through close week | DroneUp COO / Walmart VP Last-Mile Delivery |  | Complete | 100% | Gate criterion: protect. No planned schedule interruption.
Flight Operations | Day 1 | Crew schedules, maintenance program, spares inventory and dispatch procedures verified unchanged | DroneUp COO / Walmart VP Last-Mile Delivery |  | Complete | 100% | Day-1 readiness checklist — flight operations & safety.
Flight Operations | Day 30 | Full operational audit complete (fleet condition, spares, hub readiness) | DroneUp COO / Walmart VP Last-Mile Delivery |  | On Track | 60% | Feeds the Day-30 board gate: nothing unknown.
Flight Operations | Day 30 | M:N multi-drone operations roadmap approved by Steering Committee | DroneUp COO / Walmart VP Last-Mile Delivery |  | On Track | 50% | Pre-condition for the Day-100 M:N pilot.
Flight Operations | Day 100 | M:N pilot live in DFW (one operator supervising multiple aircraft) | DroneUp COO / Walmart VP Last-Mile Delivery |  | Not Started | 0% | Earn-out linked: drives cost-per-delivery glidepath.
Flight Operations | Day 100 | Validated cost-per-delivery baseline and reduction glidepath published | DroneUp COO / Walmart VP Last-Mile Delivery |  | Not Started | 0% | Validates the $30 baseline and sub-$10 trajectory.
Technology & UTM | Day 1 | ATOMx, Uncrew and AirMap-derived codebases ring-fenced; access controls verified | DroneUp CTO / Walmart Global Tech Supply-Chain Architecture Lead |  | Complete | 100% | No re-platforming decisions at Day 1.
Technology & UTM | Day 1 | IP escrow verified; no system migrations or credential changes scheduled for first 30 days | DroneUp CTO / Walmart Global Tech Supply-Chain Architecture Lead |  | Complete | 100% | Day-1 readiness checklist — technology.
Technology & UTM | Day 30 | Target integration architecture signed (store systems, order management, orchestration interfaces) | DroneUp CTO / Walmart Global Tech Supply-Chain Architecture Lead |  | On Track | 55% | Integrate at the edges, preserve the platform.
Technology & UTM | Day 30 | Walmart store-systems API specification frozen | DroneUp CTO / Walmart Global Tech Supply-Chain Architecture Lead |  | On Track | 45% | Spec freeze gates build work for the Day-100 pilot.
Technology & UTM | Day 100 | ATOMx orchestration pilot coordinating DroneUp, Wing and Zipline flights at two test sites | DroneUp CTO / Walmart Global Tech Supply-Chain Architecture Lead |  | Not Started | 0% | Earn-out linked: ATOMx integrated with Wing/Zipline ops.
Technology & UTM | Day 100 | Platform uptime ≥99.5% sustained; API integration milestones on schedule | DroneUp CTO / Walmart Global Tech Supply-Chain Architecture Lead |  | Not Started | 0% | Workstream KPI per charter §4.2.
People & Culture | Day 1 | Retention agreements executed for top ~25 regulatory- and engineering-critical staff | Walmart People Lead (M&A) / DroneUp Head of HR |  | Complete | 100% | 2–3 year vesting; signed at close, not after.
People & Culture | Day 1 | Day-1 all-hands held (DroneUp CEO + Walmart CSCO); FAQ live for ~291 employees; benefits continuity confirmed | Walmart People Lead (M&A) / DroneUp Head of HR |  | Complete | 100% | No-surprise commitments on comp and benefits.
People & Culture | Day 30 | Subsidiary organisation design confirmed; ≥90% offer acceptance on retention packages | Walmart People Lead (M&A) / DroneUp Head of HR |  | On Track | 60% | Subsidiary model preserves speed and safety culture.
People & Culture | Day 30 | Attrition watchlist and stay-interview program running | Walmart People Lead (M&A) / DroneUp Head of HR |  | On Track | 50% | Weekly IMO review of the watchlist.
People & Culture | Day 100 | Key-talent retention ≥90% achieved | Walmart People Lead (M&A) / DroneUp Head of HR |  | Not Started | 0% | Earn-out linked: key-personnel retention.
People & Culture | Day 100 | Performance and incentive framework aligned to earn-out milestones | Walmart People Lead (M&A) / DroneUp Head of HR |  | Not Started | 0% | Ties individual economics to deal economics.
Commercial & Stores Rollout | Day 1 | DFW customer experience unchanged; store-operations liaison named for each active hub | Walmart SVP Store Operations (Delivery) / DroneUp VP Operations |  | Complete | 100% | Continuity first — no customer-visible change.
Commercial & Stores Rollout | Day 1 | External announcement coordinated: press release, customer notice, partner notifications | Walmart SVP Store Operations (Delivery) / DroneUp VP Operations |  | Complete | 100% | Day-1 readiness checklist — people & communications.
Commercial & Stores Rollout | Day 30 | Store-selection criteria approved (density, airspace, demand history from the 36-hub archive) | Walmart SVP Store Operations (Delivery) / DroneUp VP Operations |  | On Track | 50% | Evidence-based site selection.
Commercial & Stores Rollout | Day 30 | 25-site expansion shortlist ratified by Steering Committee | Walmart SVP Store Operations (Delivery) / DroneUp VP Operations |  | On Track | 40% | Board approval required to go beyond the shortlist.
Commercial & Stores Rollout | Day 100 | First 5 new supercenter hubs in physical build-out | Walmart SVP Store Operations (Delivery) / DroneUp VP Operations |  | Not Started | 0% | Earn-out linked: path to 50+ locations by Month 36.
Commercial & Stores Rollout | Day 100 | DBX autonomous locker pilot live at 2 stores | Walmart SVP Store Operations (Delivery) / DroneUp VP Operations |  | Not Started | 0% | Automation lever in the delivery-cost synergy.
Regulatory & Safety | Day 1 | FAA notified of change of ownership; certificate-holding entity and named management personnel unchanged | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation |  | Complete | 100% | Certificate and its people are one asset.
Regulatory & Safety | Day 1 | SMS and manuals unchanged; single FAA point of contact named and regulatory counsel briefed | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation |  | Complete | 100% | Any certificate matter escalates immediately, no queue.
Regulatory & Safety | Day 30 | Certificate transition plan accepted by the FAA | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation |  | On Track | 65% | Day-30 gate criterion for this workstream.
Regulatory & Safety | Day 30 | Complete inventory of waivers, exemptions and expiry dates (incl. BVLOS authorisations) | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation |  | On Track | 55% | No authorisation may lapse.
Regulatory & Safety | Day 100 | Part 108 BVLOS readiness package prepared ahead of final rulemaking | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation |  | Not Started | 0% | Positions the certificate for post-rule scale.
Regulatory & Safety | Day 100 | Zero safety findings; SMS integrated into Walmart risk-governance reporting | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation |  | Not Started | 0% | Workstream KPI per charter §4.5.
Finance & Synergies | Day 1 | Funds flow executed; escrow and earn-out administration agreements live | Walmart Corporate Development Integration Finance Lead |  | Complete | 100% | Day-1 readiness checklist — legal, finance & structure.
Finance & Synergies | Day 1 | Payroll, benefits and AP/AR continuity live (TSA where required); synergy and earn-out baselines frozen | Walmart Corporate Development Integration Finance Lead |  | Complete | 100% | $30/delivery, partner rates and DFW throughput locked.
Finance & Synergies | Day 30 | Synergy register v1 complete — every initiative with owner, value estimate and evidence standard | Walmart Corporate Development Integration Finance Lead |  | On Track | 50% | See Synergy Register tab.
Finance & Synergies | Day 30 | Earn-out tracking dashboard live | Walmart Corporate Development Integration Finance Lead |  | On Track | 45% | See Earn-Out Tracker tab — one evidence base, no parallel scorekeeping.
Finance & Synergies | Day 100 | First quarterly synergy report issued to the Steering Committee | Walmart Corporate Development Integration Finance Lead |  | Not Started | 0% | Only realised value is reported to the board.
Finance & Synergies | Day 100 | FY28 run-rate synergy forecast with confidence bands | Walmart Corporate Development Integration Finance Lead |  | Not Started | 0% | Re-forecast quarterly against the glidepath.
Status seeding is illustrative: Day-1 milestones shown Complete, Day-30 On Track, Day-100 Not Started. Update Status and % Complete weekly; the Dashboard rolls up automatically.
Source: DroneUp Post-Merger Integration Plan — The First 100 Days (Walmart Corporate Development, Aug 2026), referencing DroneUp Company Profile: Strategic Fit Analysis for Walmart (May 2026). All quantities are illustrative planning values unless fixed in the plan.

## Synergy Register
Synergy Register — Categories, Owners, Value and Costs-to-Achieve
Five categories per plan §6. Baselines are frozen at close; synergies carry at Identified → Validated → Contracted → Realized, and only realised value is reported to the board. Values are illustrative planning figures ($M).
Category | Primary Lever | Owner | Stage | Timing | Annual Value Estimate ($M) | Realized to Date ($M) | Costs-to-Achieve ($M) | Net Synergy ($M) | Evidence Standard
Delivery cost reduction | M:N operations, 5-mile BVLOS radius, DBX automation | DroneUp COO / Integration Finance Lead | Validated | Recurring — Q2–Q12 | 45 | 6 | 10 |  | Cost per delivery vs. frozen $30 baseline; flight logs and hub cost actuals. Target sub-$10 by Month 18, sub-$7 by Month 36.
Partner-spend leverage | ATOMx orchestration across Wing/Zipline creates pricing transparency and negotiating leverage | Walmart VP Last-Mile Delivery | Identified | Recurring — Q3–Q8 | 12 | 1.5 | 0 |  | Per-delivery rates and contract terms vs. pre-close benchmarks; signed partner contracts.
Revenue per hub | BVLOS radius expands serviceable households ~300% per hub | Walmart SVP Store Operations (Delivery) | Identified | Recurring — Q2–Q6 | 25 | 2 | 18 |  | Orders per hub per day; households reachable per hub, measured off hub-level order data.
Avoided build cost | Owning the stack vs. an in-house build (NPV advantage per Buy-vs-Build model) | Walmart Corporate Development | Realized | One-time | 161.5 | 161.5 | 12 |  | Tracked once at close from the Buy-vs-Build model; validated against integration actuals.
New revenue options | ATOMx licensing; healthcare/pharmacy delivery via ~4,600 Walmart pharmacies | Walmart Corporate Development / DroneUp CEO | Identified | Recurring — Q4–Q12 | 18 | 0 | 0 |  | Qualified pipeline and pilot revenue; only contracted pilots count toward realised value.
TOTAL
Recurring run-rate subtotal (excludes one-time)
One-time subtotal
Costs-to-Achieve Breakdown ($M)
Retention packages (top ~25 critical staff) | 12
Hub build-outs (new supercenter hubs) | 18
Integration engineering | 10
Total costs-to-achieve
Costs-to-achieve are one-time and are netted against benefits in the same report, so the Steering Committee always sees net synergy. Annual Value Estimate for 'Avoided build cost' is a one-time NPV advantage, not a run-rate — read it with the subtotals above.
Source: DroneUp Post-Merger Integration Plan — The First 100 Days (Walmart Corporate Development, Aug 2026), referencing DroneUp Company Profile: Strategic Fit Analysis for Walmart (May 2026). All quantities are illustrative planning values unless fixed in the plan.

## Risk Register
Integration Risk Register
Score = Probability × Impact (1–5 each). RAG: score ≥15 Red, ≥8 Amber, otherwise Green. Probability and impact ratings are illustrative planning judgements; risks and mitigations are drawn from plan §8.
# | Risk | Workstream | Probability (1-5) | Impact (1-5) | Score | RAG | Mitigation | Owner | Review Cadence
1 | Key-talent flight — regulatory-critical personnel and platform engineers depart post-close, degrading both the Part 135 certificate and the technology asset | People & Culture | 3 | 5 |  |  | Retention packages with 2–3 year vesting signed at close for the top ~25; earn-out ties founder/leadership economics to staying; attrition watchlist with weekly IMO review | Walmart People Lead (M&A) / DroneUp Head of HR | Weekly — IMO
2 | FAA certificate disruption — change of ownership triggers certificate review; a lapse in named personnel or SMS continuity impairs operating authority | Regulatory & Safety | 2 | 5 |  |  | No Day-1 changes to the certificate-holding entity, accountable executives or safety systems; proactive FAA engagement pre- and post-close; Regulatory & Safety gate at Day 30 | DroneUp Chief Pilot (Accountable Executive) / Walmart Chief Counsel – Aviation | Weekly — immediate escalation to Steering Committee chair
3 | Unit economics fail to improve — the ~$30/delivery structure that ended the partnership persists, undermining the scaling thesis | Flight Operations | 3 | 4 |  |  | Expansion gated on demonstrated cost milestones; M:N pilot by Day 100; cost-per-delivery glidepath validated by Flight Operations and re-forecast quarterly by Finance | DroneUp COO / Walmart VP Last-Mile Delivery | Bi-weekly — Steering Committee
4 | Integration smothers the asset — premature absorption into Walmart processes and systems slows engineering velocity and triggers cultural attrition | People & Culture / Technology & UTM | 3 | 4 |  |  | Subsidiary operating model preserved through Year 1; integration limited to defined interfaces; IMO acts as the single point of Walmart demand on DroneUp teams | IMO Integration Lead | Bi-weekly — IMO
5 | Partner-channel friction — Wing and Zipline resist coordination through a Walmart-owned ATOMx layer, or deprioritize Walmart volume | Commercial & Stores / Technology & UTM | 3 | 3 |  |  | Position ATOMx as vendor-neutral orchestration benefiting all operators; maintain both partnerships commercially through integration; sequence the orchestration pilot at low-stakes test sites first | Walmart SVP Store Operations | Bi-weekly — IMO
6 | Narrative / communications risk — scrutiny of the prior Virginia-market track record shapes employee, customer and partner perception of the deal | Commercial & Stores Rollout | 3 | 3 |  |  | Coordinated Day-1 external announcement (press release, customer notice, partner notifications); manager talking points and employee FAQ; evidence-led external messaging tied to demonstrated cost and safety milestones rather than expansion promises | Walmart SVP Store Operations (Delivery) / Corporate Affairs | Bi-weekly — IMO
7 | Cybersecurity — aviation and airspace-management systems (ATOMx, Uncrew) exposed during integration; credential or access-control failures carry safety as well as data consequences | Technology & UTM | 2 | 5 |  |  | Codebases ring-fenced with verified access controls and IP escrow at Day 1; no system migrations or credential changes in the first 30 days; cybersecurity posture review at Day 15 with aviation systems in scope | DroneUp CTO / Walmart Global Tech Security | Weekly — IMO until Day 30 review closes
Open risks scored Red
Open risks scored Amber
Highest residual score
Register now covers all five risks from plan §8 plus narrative/communications and cybersecurity. Probability and impact ratings are illustrative planning judgements calibrated to the impact levels stated in the plan (High = 5, Medium–High = 4, Medium = 3); Score and RAG are formulas.
Source: DroneUp Post-Merger Integration Plan — The First 100 Days (Walmart Corporate Development, Aug 2026), referencing DroneUp Company Profile: Strategic Fit Analysis for Walmart (May 2026). All quantities are illustrative planning values unless fixed in the plan.

## Earn-Out Tracker
Earn-Out Tracker — Consideration at Risk and Milestone Status
The earn-out is tied to cost-per-delivery milestones, ATOMx integration with Wing/Zipline operations, 50+ store scaling and key-personnel retention (plan §1). Pool allocation across milestones is illustrative.
Consideration Structure
Component | $M | % of Total | Basis
Total consideration |  |  | Assumptions tab, input cell B9
Cash at close |  |  | Formula: total × cash share (Assumptions B10)
Earn-out pool |  |  | Formula: total × earn-out share; plan §1 states 30–40% of consideration
Earn-Out Milestones
# | Milestone | Measurement Basis | Target Date | Consideration at Risk ($M) | % of Earn-Out Pool | Status | Notes
1 | Cost per delivery below $10.00 by Month 18 | Trailing three-month fully-loaded cost per delivery vs. the $30 baseline frozen in the close model; measured from flight logs and hub cost actuals |  | 25 |  | In Progress | Contractual gate 1. Glidepath shows $9.50 at Month 18 against a $10.00 threshold — minimal headroom.
2 | Cost per delivery below $7.00 by Month 36 | Same basis as gate 1, measured at Month 36 |  | 25 |  | Not Started | Contractual gate 2. Glidepath shows $6.80 against a $7.00 threshold.
3 | ATOMx integrated with Wing and Zipline operations | ATOMx orchestrating live DroneUp, Wing and Zipline flights across agreed sites without airspace conflict, on the production orchestration layer |  | 15 |  | In Progress | Day-100 milestone proves the pilot at two test sites; target date for full operational integration is illustrative.
4 | 50+ Walmart locations operating on DroneUp technology | Count of live Walmart locations with DroneUp-operated or DroneUp-platform delivery, verified from hub operating records |  | 15 |  | Not Started | First 5 new supercenter hubs enter build-out at Day 100; gated on demonstrated cost milestones.
5 | Key-personnel retention through vesting | Retention of the top ~25 regulatory- and engineering-critical staff through the 2–3 year vesting period, measured against the close-date roster |  | 10 |  | In Progress | Day-100 target is ≥90% retention; long-term target is ≥85% through earn-out vesting.
TOTAL | Total consideration at risk
Tie-out to earn-out pool
Earn-out as % of total consideration
Allocation of the pool across the five milestones (25 / 25 / 15 / 15 / 10) is an illustrative planning split, not a term sheet. Target dates key off the Close Date on the Assumptions tab.
Source: DroneUp Post-Merger Integration Plan — The First 100 Days (Walmart Corporate Development, Aug 2026), referencing DroneUp Company Profile: Strategic Fit Analysis for Walmart (May 2026). All quantities are illustrative planning values unless fixed in the plan.

## Assumptions
Assumptions & Inputs — DroneUp PMI Tracker
Amber cells are inputs. Everything else in this workbook keys off them — change the Close Date and every milestone date re-flows.
Deal & Timing Inputs
Item | Value | Unit / Format | Source / Basis
Close Date (Day 1) | 2026-09-01 | date | Planning assumption stated in plan §5 (close-date callout)
Day 30 Gate |  | date | Formula: Close Date + 29 days (plan §5 = 2026-09-30)
Day 100 Gate |  | date | Formula: Close Date + 99 days (plan §5 = 2026-12-09)
Total consideration | 250 | $M | Illustrative deal value per delegated task brief
Cash at close (% of total) | 64% | % | Illustrative; plan §1 states earn-out is 30–40% of consideration
Earn-out (% of total) |  | % | Formula: 1 less cash share
Cash consideration |  | $M | Formula: total × cash share
Earn-out pool |  | $M | Formula: total × earn-out share — drives Earn-Out Tracker allocation
Cost per delivery — baseline at close | 30 | $/delivery | Plan §1 / §7: ~$30 baseline frozen in the close model
Employees to stabilise | 291 | headcount | Plan §1: ~291 DroneUp employees
Retention population (critical staff) | 25 | people | Plan §1 / §4.3: top ~25 regulatory- and engineering-critical staff
Key-talent retention target (Day 100) | 90% | % | Plan §4.3 / §7: ≥90% key-talent retention
Store locations target (Month 36) | 50 | locations | Plan §7: 50+ locations by Month 36
Avoided build cost (NPV advantage) | 161.5 | $M one-time | Plan §6: $161.5M NPV advantage per Buy-vs-Build model
Cost-per-Delivery Glidepath (Illustrative Planning Curve)
Milestone | Date | Cost per Delivery ($) | Target Threshold ($)
Close (baseline) |  | 30 | 30
Day 100 |  | 24 | 30
Month 12 |  | 14 | 10
Month 18 (earn-out gate 1) |  | 9.5 | 10
Month 24 |  | 8 | 10
Month 36 (earn-out gate 2) |  | 6.8 | 7
Glidepath values are the illustrative planning curve in plan §7; contractual gates are sub-$10 by Month 18 and sub-$7 by Month 36.
Source: DroneUp Post-Merger Integration Plan — The First 100 Days (Walmart Corporate Development, Aug 2026), referencing DroneUp Company Profile: Strategic Fit Analysis for Walmart (May 2026). All quantities are illustrative planning values unless fixed in the plan.